## Sheet1
Task	Notes	Est. Time (hrs)	Time Spent So far	Status	Deadline	Date Completed	Completed?	Time Taken (hrs)
Get PaperZD	it has STATE MACHINES for PAPER2D!!	1	1		2026-01-23	2026-01-23	1	1
Refactor for PZD		15	1		2026-01-23	2026-01-23	1	1
Learn PZD	tutorials from https://www.youtube.com/watch?v=_8KWl0is2eI&list=PLf0WtSu4PG-MAiE32vQsFV1icMNhz6wGu&index=13	15	1	ongoing
Spawn teams in GM		7	5
AI – go to faceoff spot		3	2
Have players possess pawns	player selects team / (optional) player selects position / Player now controlling pawn	15
get Remote Play working	use miniPC to test	22