## Sheet1
Task	Notes	Est. Time (hrs)	Time Spent So far	Status	Deadline	Date Completed	Completed?	Time Taken (hrs)
Get PaperZD	it has STATE MACHINES for PAPER2D!!	1	1		2026-01-23	2026-01-23	1	1
Refactor for PZD		15	1		2026-01-23	2026-01-23	1	1
Learn PZD	tutorials from https://www.youtube.com/watch?v=_8KWl0is2eI&list=PLf0WtSu4PG-MAiE32vQsFV1icMNhz6wGu&index=13	15	1	ongoing
Spawn teams in GM		7	5
AI – go to faceoff spot		3	2
Have players possess pawns	player selects team / (optional) player selects position / Player now controlling pawn	15
get Remote Play working	use miniPC to test	22
Rework AI GoTo logic		22

## log
StartTime	EndTime	Task	notes
09:03:09	10:06:17	AI movement and stopping
10:36:11	14:19:22	AI movement and stopping	-1 hr lunch
14:54:31	16:20:06	Ai movement like flee and pursue	i dont think there is any way around this, steering behaviours need to be reworked / Right now it is using an “intended” direction / But its just annoying to deal with when there are competing steering desires